Inside Sets — Design Framework (Before Questions)

Guiding Principles (LOCKED)

These principles apply to all Inside Set questions and scope language:

Customer access drives productivity
→ Contractors cannot control completion without customer response.

Route closure ≠ 100% installs
→ Route completion must explicitly account for:

- No response

- Refusals

- Vacant properties

- Safety or access constraints

RTU/UIR still apply, but:
→ Many Inside Set issues are customer-side, not infrastructure-side.
→ These must be categorized separately from PIT RTUs.

Appointment-based work is probabilistic, not linear
→ Expectations must be set accordingly in scope language.

Inside Sets Banner (Top of Section – Required)

Indoor meter installations are dependent on customer response and access. Route completion, productivity, and progression should account for no-response, refusals, and access limitations beyond the contractor’s control.

Inside Sets — Section I

Program Applicability & Scale

I1) Inside Set Inclusion

Question
Does this project include indoor water meter installations?

☐ Yes — majority of meters
☐ Yes — limited subset
☐ No
☐ Not sure

Effect

- If “No” → Entire Inside Set section suppressed

- If “Limited subset” → Lower productivity assumptions + special routing

Notes (optional)

I2) Estimated Inside Set Volume

Question
Approximately what percentage of total meters are indoor installations?

☐ <10%
☐ 10–25%
☐ 25–50%
☐ >50%
☐ Unknown

Guidance (collapsed)
Higher indoor percentages materially impact scheduling, staffing, and customer coordination.

Notes (optional)

I3) Property Types

Question
What types of properties contain indoor meters? (Multi-select)

☐ Single-family residential
☐ Multi-family residential
☐ Commercial
☐ Mixed-use
☐ Institutional (schools, hospitals, etc.)
☐ All / predominantly indoor system

Effect
MDU + commercial → separate scheduling logic later

Notes (optional)

Inside Sets — Section II

Customer Scheduling & Appointments

I4) Scheduling Responsibility

Question
Who is responsible for customer outreach and appointment scheduling for indoor meter installations?

☐ Utility-led (contractor supports)
☐ Contractor-led (utility supports)
☐ Shared responsibility
☐ Not defined

Best practice (collapsed)

- Utility sends an initial project announcement letter on utility letterhead.

- Contractor manages appointment requests and follow-up attempts (mail/phone/text as defined).

- After a defined non-response threshold, accounts escalate to Utility Intervention Required (UIR).

Notes (optional)

I4a) Outreach Sequence & Touchpoints

Question
What outreach sequence is required before an account is classified as no-response / escalated?

☐ Utility letter + 1–2 contractor contacts
☐ Utility letter + 3–4 contractor contacts (recommended)
☐ Utility letter + 5+ contractor contacts
☐ Not defined

Best practice (collapsed)
Initial utility letter, then three mailed attempts with increasing urgency. Optional final door hanger may be used at additional cost.

Cost note (collapsed)
Door hangers and in-person attempts add significant labor cost compared to mailed outreach.

Notes (optional)

I4b) Contractor “Turn-Off Point”

Question
After how many unsuccessful attempts should the contractor stop attempting and escalate the account?

☐ After a defined number of attempts
☐ After a defined time window (e.g., 30–60 days)
☐ Utility discretion
☐ Not defined

Guidance (collapsed)
Contractors should not be expected to perform unlimited reattempts for non-responsive customers.

Notes (optional)

I4c) Utility Intervention Required (UIR) Actions

Question
Once escalated to UIR, what actions may the utility use to secure access? (Multi-select)

☐ Utility-led outreach / official notice process
☐ Schedule appointment through utility channel
☐ Service shutoff / service hold procedures (where allowed)
☐ Fees/charges for non-compliance (where allowed)
☐ Case-by-case
☐ Not defined

Notes (optional)

I5) Appointment Window Standard

Question
What appointment window structure will be used?

☐ 2-hour windows
☐ 4-hour windows (recommended)
☐ All-day windows
☐ Other / not defined

Best practice (collapsed)
2–4 hour windows balance customer convenience with route flexibility and allow crews to absorb cancellations.

Notes (optional)

I6) Call Center & Dispatch Capability

Question
Will contractor-provided call center and dispatch capability be required for indoor scheduling?

☐ Yes
☐ No
☐ Shared with utility
☐ Not sure / not defined

Conditional follow-ups

- Required hours of coverage

- Required languages

- Ability to fill same-day cancellations (Yes/No)

Best practice (collapsed)
Larger indoor programs benefit from a scheduling “command center” to fill cancellations and improve completion rates.

Notes (optional)

RFP Requirement (Informational Panel – Not a Question)

Bidders shall propose expected indoor productivity (installs/crew/day) and assumptions (appointment success rate, travel time, property types), and include staffing plan.

I7) Missed Appointments Handling

Question
How should missed appointments be handled and compensated?

☐ Included in unit price (contractor absorbs)
☐ Separate line item fee after defined threshold
☐ Returned to utility after first miss
☐ Not defined

Best practice (collapsed)
One courtesy reschedule is common; repeated misses should trigger defined fees or escalation.

Notes (optional)

Inside Sets — Section III

Notifications & Customer Engagement

I8) Notification Channels

Question
Which notification channels are authorized for indoor access scheduling? (Multi-select)

☐ Utility letterhead letter (recommended)
☐ Contractor postcard(s)
☐ Phone calls
☐ Text messages
☐ Email
☐ Door hanger (higher cost)
☐ In-person door knock (higher cost)
☐ Not defined

Notes (optional)

I8a) Addressing Rules

Question
For mailed notifications, where should notices be sent?

☐ Service address only
☐ Billing/mailing address only
☐ Both service + billing/mailing (recommended)
☐ Not defined

Guidance (collapsed)
Commercial and absentee-owner accounts may not receive mail at the service address.

Notes (optional)

I8b) Walk-In Required Flags

Question
Can the utility identify accounts where mailed outreach is unlikely to reach the occupant and in-person contact is required?

☐ Yes (flagged list available)
☐ Somewhat
☐ No
☐ Not sure

Notes (optional)

I9) Number of Contact Attempts

Question
How many contact attempts should be made before classifying an account as no-response?

☐ 1–2
☐ 3–4
☐ 5+
☐ Not defined

Guidance (collapsed)
Best practice includes multiple contact attempts across different channels.

I10) No-Response Classification

Question
When should a location be classified as no-response or customer unavailable?

☐ After defined number of attempts
☐ After a defined time period
☐ At utility discretion
☐ Not defined

Effect
No-response → Inside Set RTU (customer-driven)

Inside Sets — Section IV

Route Closure & Progression

I11) Route Closure Definition (Inside Sets)

Question
Which dispositions should count toward route completion for indoor work? (Multi-select)

☐ Completed install
☐ Customer refusal documented
☐ No-response documented
☐ Vacant/unoccupied documented
☐ Safety/access constraint documented
☐ Utility Intervention Required (UIR) created
☐ Return to Utility (RTU) created

Guidance (collapsed)
Indoor route closure must be based on documented outcomes, not 100% installs.

Notes (optional)

I12) Progression Protection

Question
If remaining open locations are no-response, refusal, or UIR-dependent, may the contractor advance to new routes?

☐ Yes (recommended)
☐ No
☐ Subject to approval
☐ Not defined

Notes (optional)

Inside Sets — Section V

Customer Refusals & Liability

I13) Customer Refusals

Question
How should customer refusals be handled?

☐ Logged and returned to utility
☐ Escalated through utility outreach
☐ Considered complete for contractor scope
☐ Not defined

Notes (optional)

I14) Interior Damage & Leak Liability

Question
How should responsibility be assigned for leaks or damage associated with indoor installations?

☐ Contractor responsible for installation workmanship (recommended baseline)
☐ Utility responsible for pre-existing plumbing failures
☐ Shared / case-by-case with defined criteria
☐ Not defined

Best practice (collapsed)
Contractor is responsible for workmanship-related issues. Pre-existing failures outside contractor control (e.g., brittle lead or galvanized lines not disturbed) should follow defined utility contingency.

Notes (optional)

I14a) Lead Service Line Presence

Question
Are lead or lead-adjacent service lines expected?

☐ Yes
☐ No
☐ Unknown

Guidance
If yes/unknown → define special procedures and shared-risk escalation; recommend audit/field validation.

Inside Sets — Section VII

Water Shutoff, Valves & Service Isolation

Global Guidance (collapsed)

Uncertainty around valves, curb stops, and access introduces contractor risk, typically reflected in higher unit pricing. Clear responsibility and contingency definitions improve bid competitiveness and reduce disputes.

I15) Primary Shutoff Method

Question
What is the expected primary method for shutting off water during indoor meter replacement?

☐ Interior shutoff valve only
☐ Curb stop (B-Box) only
☐ Interior valve preferred; curb stop as backup (recommended)
☐ Not defined

I16) Interior Shutoff Valve Condition

Question
What is the general condition of interior shutoff valves?

☐ Generally reliable
☐ Mixed condition
☐ Frequently inoperable
☐ Unknown

I16a) Interior Shutoff Valve Type

Question
What types of interior shutoff valves are typically present? (Multi-select)

☐ Ball valves
☐ Gate valves
☐ Globe valves
☐ Mixed / varies
☐ Unknown

I16b) Interior Valve Replacement Contingency

Question
If an interior shutoff valve is non-functional, is replacement authorized?

☐ Yes — included in installation scope
☐ Yes — under contingency allowance
☐ No — utility responsibility
☐ Not defined

I17a) Curb Stop (B-Box) Asset Data Availability

Question
Does the utility maintain asset-level data identifying curb stop locations?

☐ Yes — accurate and current
☐ Partial / limited accuracy
☐ No
☐ Not sure

I17b) Curb Stop Accessibility Condition

Question
What is the general accessibility condition of curb stops?

☐ Generally accessible
☐ Mixed condition
☐ Frequently buried / obstructed
☐ Unknown

I18) Authorization to Operate Curb Stops

Question
Is the installation contractor authorized to access and operate curb stops?

☐ Yes
☐ Yes — with limitations
☐ No — utility staff only
☐ Not defined

I18a) Utility-Performed Curb Stop Operations

Question
If utility-performed, what is the expected response time?

☐ Same-day
☐ Next-day
☐ Scheduled
☐ Not defined

I18b) Contractor-Performed Curb Stop — Cost Treatment

Question
How should contractor curb stop access be treated commercially?

☐ Included in unit price
☐ Separate contingency line item (recommended)
☐ Time & materials
☐ Not defined

I20) Valve Replacement Standards

Question
If valve replacement is authorized, are there utility standards?

☐ Specific valve/model required
☐ General specifications provided
☐ Contractor standard acceptable
☐ Not defined

I21) Freeze Kits / Alternative Isolation

Question
Are freeze kits or alternative isolation methods permitted?

☐ Yes
☐ No
☐ Only with utility approval
☐ Not applicable
☐ Not defined

I24) Emergency Leak Response

Question
If a leak occurs during or immediately after installation, what is the expected response?

☐ Contractor mitigates
☐ Utility dispatches emergency crew
☐ Shared response
☐ Not defined

I25) Post-Install Water Restoration Verification

Question
What verification is required before restoring service? (Multi-select)

☐ Visual leak check
☐ Pressure stabilization
☐ Customer confirmation
☐ Documentation/photo
☐ Not defined